## Cover Page
Big Data Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today | 2025-07-09
Project Team Name | Group 2
Project Topic | Phân tích dữ liệu tiêu thụ năng lượng
Task |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[7 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[7 empty] | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20
1. Tạo dữ liệu Input |  | 2025-07-09 | 23h59',18/7/2025 |  |  | In-progress | bar: 2021-11-01 to 2021-11-13
2. Xây dựng chương trình tạo biểu đồ về mức tiêu thụ năng lượng |  | 2025-07-09 | 23h59',25/7/2025 |  |  | In-progress | bar: 2021-11-01 to 2021-11-12
3. Xây dựng chương trình dự đoán mức tiêu thụ năng lượng trong tương lai |  | 2025-07-09 | 23h59',25/7/2025 |  |  | In-progress | bar: 2021-11-01 to 2021-11-08
4.Tìm cách giảm mức tiêu thụ năng lượng |  | 2025-07-09 | 23h59', 1/8/2025 |  |  | In-progress | bar: 2021-11-01 to 2021-11-06
5. Hoàn thiện Báo cáo |  | 2025-07-09 | 23h59', 3/8/2025 |  |  | In-progress
6. Hoàn thiện Slides |  | 2025-07-09 | 23h59', 3/8/2025 |  |  | In-progress
In-progress
In-progress
In-progress
In-progress
In-progress
In-progress
In-progress
In-progress
In-progress
In-progress